## Tabelle1
Tasks | Action | status | completed Data | required for
Investigation of different types of petri nets and find which is suitable for the IDE4L modelling | literature review | 5 % | 29.05
Definition of the actors, functions and relations in IDE4L | Self-summary | 20 % | 12.06
Learn different automation systems and select two to run IDE4L | literature review | 30 % | 26.06
Study different tools of petri nets | literature review | 40 % | 10.07
Implement petri nets to represent the automations system | development | 45 % | 17.07
Draw the graphical representation in petri nets | development | 55 % | 31.07
Test and simulation | development | 65 % | 14.08
Comparison 2 models and choose one | development | 70 % | 21.08
Qualitative analysis and conclusions | development | 75 % | 28.08
Thesis first draft | written | 80 % | 02.10
Abhi’s review | review | 90 % | 16.10
Final Presentation | presentation | 95 % | 23.10
End thesis | review | 100 % | 30.10